## Dashboard
Change Order Dashboard
Know your exposure. Close the open ones.
| Open (Pending) COs | Approved · Not Billed
| 0 | 0
| Total Approved CO Cost | Total Approved CO Price
| 0 | 0
| Total Approved CO Profit | Blended Margin
| 0 | 0%
THE 5 CHANGE-ORDER RULES WE LIVE BY
1. No work starts on a change until the customer signs. Verbal is not signed. Text is signed enough if you save the thread.
2. Margin on a change order should be HIGHER than base contract (target 27%+). You're already on-site — no new mob cost, no new sales expense.
3. If it's a change your subs caused (not the owner): log it, but eat it. Don't bill the owner for your own rework.
4. Bill COs separately on the next draw request so the customer sees them line-itemed.
5. Monday review: any Pending over 7 days? Call today. Friday review: any Approved + Billed=No? Invoice before you close the week.
Built by Salisbury Bookkeeping · salisburybookkeeping.com · topbuildercfo.com · (385) 374-9295

## Log
Change Order Log
Log every change the week it happens · review weekly
| Date Initiated | CO # | Job # | Job Name | Description | Status | Cost Impact | Price Impact | Margin | Days Impact | Approved By | Approval Date | Billed? | Paid?
| 2026-01-15 | 001 | 1001 | Smith Custom Home | Upgrade kitchen cabinets to custom | Approved | 8500 | 12000 | 0% | Sarah Smith | 2026-01-18 | Yes | Yes
| 2026-01-22 | 002 | 1001 | Smith Custom Home | Add mini-split to sunroom | Approved | 3200 | 4500 | 0% | Sarah Smith | 2026-01-24 | Yes | No
| 2026-01-29 | 003 | 1002 | Jones Addition | Owner changed flooring selection | Approved | 1800 | 2400 | 0% | Mike Jones | 2026-02-01 | Yes | Yes
| 2026-02-05 | 004 | 1002 | Jones Addition | Structural beam for new opening | Pending | 4200 | 5800 | 0%
| 2026-02-12 | 005 | 1003 | Acme Office | Extra data drops in conference room | Rejected | 650 | 900 | 0%
| 2026-02-19 | 006 | 1003 | Acme Office | Additional restroom | Approved | 14000 | 19500 | 0% | Bob Allen | 2026-02-22 | No | No
| 2026-03-02 | 007 | 1004 | Cedar Ridge Townhomes | Upgrade to LVP flooring throughout | Approved | 11500 | 16800 | 0% | Cedar Ridge PM | 2026-03-04 | Yes | No
| 2026-03-11 | 008 | 1004 | Cedar Ridge Townhomes | Add smart-home prewire package | Pending | 5200 | 8500 | 0%
| 2026-03-18 | 009 | 1005 | Miller Bath Remodel | Move plumbing wall 18 inches | Approved | 2400 | 3600 | 0% | Miller Family | 2026-03-20 | Yes | Yes
0%
0%
0%
Built by Salisbury Bookkeeping · salisburybookkeeping.com · topbuildercfo.com · (385) 374-9295
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%