## WIP Schedule
WIP Schedule — Percentage of Completion
The same format BuilderCFO ships to clients · bank-ready
| Job # | Job Name | Customer | Contract Amount | Approved COs | Revised Contract | Est. Total Cost | Cost to Date | Est. Cost to Complete | % Complete | Earned Revenue | Billed to Date | Over / (Under) Billing
| 1001 | Smith Custom Home | Smith Family | 850000 | 24500 | 874500 | 710000 | 455000 | 255000 | 64.08% | 0 | 510000 | 0
| 1002 | Jones Addition | Jones LLC | 210000 | 0 | 210000 | 168000 | 134000 | 34000 | 79.76% | 0 | 180000 | 0
| 1003 | Acme Office Buildout | Acme Corp | 475000 | 18000 | 493000 | 396000 | 98000 | 298000 | 24.75% | 0 | 140000 | 0
| 1004 | Cedar Ridge Townhomes | Cedar Ridge LLC | 1240000 | 62000 | 1302000 | 1045000 | 812000 | 233000 | 77.7% | 0 | 825000 | 0
| 1005 | Miller Bath Remodel | Miller Family | 68000 | 4200 | 72200 | 52000 | 48000 | 4000 | 92.31% | 0 | 42000 | 0
| TOTAL | 5 jobs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0
How to read the Over / (Under) Billing column
• POSITIVE (green) = OVERBILLED. You've billed more than you've earned. It's a liability on your balance sheet; don't spend it — it belongs to the job.
• NEGATIVE (red) = UNDERBILLED. You've earned more than you've billed. File a progress bill THIS WEEK — that money is yours.
• Owner-pushed change orders that aren't in the Revised Contract column yet = invisible underbilling. Chase the signature.
• If Est. Cost to Complete keeps rising job-over-job — your estimator is systematically under-bidding. Fix it in the next 3 bids.
• Banker tip: surety underwriters read this schedule before they read your P&L. Clean WIP = higher bonding capacity.
• BuilderCFO auto-computes this from your QuickBooks / Xero data nightly. See topbuildercfo.com.
Built by Salisbury Bookkeeping · salisburybookkeeping.com · topbuildercfo.com · (385) 374-9295

## Bank Package Prep
Bank / Surety Package Checklist
What to attach when you hand this schedule to your banker or bonding agent
| ✓ | Item
| ☐ | This WIP Schedule, exported as PDF (File → Save As PDF, Landscape, Fit to Width)
| ☐ | Most recent month-end P&L (accrual basis)
| ☐ | Most recent month-end Balance Sheet
| ☐ | AR Aging by Job (detail, not summary)
| ☐ | AP Aging by Vendor
| ☐ | Schedule of Values for each open job (if the bank asks)
| ☐ | Copy of current bonding rider + remaining capacity
| ☐ | 12-month trailing revenue trend (one line chart is enough)
| ☐ | Your 13-week cash forecast — free template at salisburybookkeeping.com/tools
| ☐ | Current credit line balance + limit
| ☐ | Insurance certificates (GL, WC, Auto, Umbrella) — all current
| ☐ | For each job: estimated completion date + est. final gross margin %
Built by Salisbury Bookkeeping · salisburybookkeeping.com · topbuildercfo.com · (385) 374-9295